Task 3

Risk management plan

|  |  |  |  |
| --- | --- | --- | --- |
| Risk | Category | Reason | Contingency |
| Absenteeism | Mitigate | It will delay the speed of service to customers | We will add two more customers to ensure we don’t loss customers |
| Failerstove | Mitigate | It will slower the process of producing product | We have another stove a backup.  We have someone who do maintenance at store. |
| Stock shortage | Mitigate | It will slower the process of producing product | We stock enough stock.  We borrow stock from another store. |
| Resignation | Mitigate | It will delay the process and increase cost | They must give notice of resignation in advance |
| RGM resigning | Avoid | Do not have powers to stop the action of resigning | We will appoint another RGM highly possible from the manager someone who have a idea of the project |
| Process change | Avoid | We depend on functionality | This will be done by trainers |
| Financial risk | Mitigate | It will increase the cost | Will be more amount added on project |